## Implementation Tracker
Tax Ready Implementation Tracker
Week | Phase | Task | Owner | Start Date | Due Date | Status | Notes
1 | Foundation | Review current COA |  |  |  | Not Started
1 | Foundation | Document account structure |  |  |  | Not Started
2 | Foundation | Clean up inactive accounts |  |  |  | Not Started
2 | Foundation | Set up account numbers |  |  |  | Not Started
3 | Vendors | Audit vendor list |  |  |  | Not Started
3 | Vendors | Collect missing W-9s |  |  |  | Not Started
4 | Vendors | Verify TINs |  |  |  | Not Started
4 | Policies | Document invoice policy |  |  |  | Not Started
5 | Policies | Document expense policy |  |  |  | Not Started
5 | Policies | Create approval workflows |  |  |  | Not Started
6 | Controls | Implement segregation of duties |  |  |  | Not Started
6 | Controls | Set up bank reconciliation |  |  |  | Not Started
7 | Automation | Identify automation candidates |  |  |  | Not Started
7 | Automation | Configure rules |  |  |  | Not Started
8 | Testing | Test workflows |  |  |  | Not Started
8 | Testing | Validate controls |  |  |  | Not Started
9 | Training | Train team on policies |  |  |  | Not Started
9 | Training | Document procedures |  |  |  | Not Started
10 | Rollout | Go live with automation |  |  |  | Not Started
10 | Rollout | Monitor compliance |  |  |  | Not Started
11 | Review | First compliance review |  |  |  | Not Started
11 | Review | Adjust as needed |  |  |  | Not Started
12 | Optimize | Final review |  |  |  | Not Started
12 | Optimize | Plan next quarter |  |  |  | Not Started
© 2026 ProjectBits Consulting. All rights reserved.